## Technical Risks
ID | Risk | Probability | Impact | Risk Score | Mitigation | Status
T1 | AI performance at 100+ agents | High (70%) | 10 |  | LOD, tick budgeting | Open
T2 | Multiplayer desync issues | Medium (50%) | 10 |  | Deterministic sim | Open
T3 | Database performance | Medium (40%) | 8 |  | Caching, optimization | Open
T4 | Memory leaks | Medium (40%) | 8 |  | Profiling, pooling | Open

## Design Risks
ID | Risk | Probability | Impact | Risk Score | Mitigation
D1 | AI behavior feels robotic | High (65%) | 9 |  | Multiple brain configs
D2 | Governance too complex | Medium (50%) | 8 |  | Progressive disclosure
D3 | Not fun | Medium (40%) | 10 |  | Early playtesting
D4 | Economy broken | High (60%) | 8 |  | Data-driven balancing
D6 | Scope creep | High (70%) | 7 |  | Strict MVP definition

## Decision Gates
Gate | Criteria | Go Criteria | No-Go Action
Proto 1 | World simulation | 60+ FPS, stable | Optimize or change engine
Proto 2 | AI authentic | 70%+ feels alive | Simplify AI
Proto 3 | Governance usable | 50%+ engagement | Cut governance scope
Proto 4 | Progression engaging | 60%+ defeat meteor | Adjust difficulty
Alpha | Complete loop | 3+ hour sessions | Major revision

## Dashboard
Risk Category | Count | Average Score | Priority
Critical (>6.0) |  | High | Immediate action
High (4.0-6.0) |  | Medium | Action needed
Medium (2.5-4.0) |  | Low | Monitor